## Sprint 1 & 2 Burndown
Sprint 1
Date | Days | Actual | Ideal
N/A | 0 | 78 | 78
2018-03-28 | 1 | 78 | 78
2018-03-29 | 2 | 78 | 78
2018-03-30 | 3 | 78 | 78
2018-03-31 | 4 | 78 | 78
2018-04-01 | 5 | 78 | 78
2018-04-02 | 6 | 78 | 78
2018-04-03 | 7 | 78 | 58
2018-04-04 | 8 | 78 | 58 | *
2018-04-15 | 9 | 78 | 58 | *
2018-04-16 | 10 | 78 | 58
2018-04-17 | 11 | 78 | 58
2018-04-18 | 12 | 78 | 58
2018-04-19 | 13 | 78 | 58
2018-04-20 | 14 | 78 | 38
2018-04-21 | 15 | 78 | 38
2018-04-22 | 16 | 78 | 38
2018-04-23 | 17 | 78 | 38
2018-04-24 | 18 | 78 | 38
2018-04-25 | 19 | 51 | 38
2018-04-26 | 20 | 51 | 38 |  | Observation:
2018-04-27 | 21 | 51 | 18 |  | 1. We were behind schedule for most of Sprint 1 - we note this may be due to us learning about Django, Python etc.
2018-04-28 | 22 | 51 | 18 |  | 2. Only 7 uncomplete tasks
2018-04-29 | 23 | 40 | 18 |  | 3. Tasks are done in 'chunks'
2018-04-30 | 24 | 40 | 18
2018-05-01 | 25 | 40 | 18
2018-05-02 | 26 | 7 | 0
*5 April --> 14 April was Mid-Sem Break
Sprint 2
Date | Days | Actual | Ideal
N/A * | 0 | 50 | 50
2018-05-02 | 1 | 50 | 50
2018-05-03 | 2 | 50 | 50
2018-05-04 | 3 | 50 | 50
2018-05-05 | 4 | 50 | 50
2018-05-06 | 5 | 50 | 50
2018-05-07 | 6 | 50 | 50
2018-05-08 | 7 | 50 | 50
2018-05-09 | 8 | 43 | 35
2018-05-10 | 9 | 43 | 35
2018-05-11 | 10 | 43 | 35
2018-05-12 | 11 | 43 | 35
2018-05-13 | 12 | 43 | 35
2018-05-14 | 13 | 43 | 35
2018-05-15 | 14 | 35 | 35
2018-05-16 | 15 | 31 | 20
2018-05-17 | 16 | 31 | 20
2018-05-18 | 17 | 4 | 20
2018-05-19 | 18 | 4 | 20
2018-05-20 | 19 | 4 | 20 |  | Observation:
2018-05-21 | 20 | 4 | 20 |  | 1. At around 17 days, we were ahead of schedule
2018-05-22 | 21 | 4 | 20 |  | 2. Finished all tasks on the 23rd of May
2018-05-23 | 22 | 0 | 5 |  | 3. "Chunks" of tasks were more frequent
2018-05-24 | 23 | 0 | 5 |  | 4. 2 Stories and 11 redundant tasks were removed
2018-05-25 | 24 | 0 | 5
2018-05-26 | 25 | 0 | 5
2018-05-27 | 26 | 0 | 5
2018-05-28 | 27 | 0 | 5
2018-05-29 | 28 | 0 | 5
2018-05-30 | 29 | 0 | 0
*18 tasks were removed
Original total tasks for S-2 was 68

## Release Burndown
Release Burndown
Sprints Completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 187 | 187
1 | 47 | 43
2 | 0 | 0
* less removed stories
Observation:
1. Majority of Stories completed in Sprint 1
2. All stories but 22 and 23 were completed by end of Sprint 2
3. Finished ahead of expected schedule