## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 137 | 137
1
2 | 0
3 | 0
4 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 130 | 130
19
18
17
16
15
14
13
12
11
10
9
8
7
6
5
4
3
2
1
0 | 0
ALSO DO A SPRINT 2 BURNDOWN AS WELL
Sprint 1 started in W6
IDEAL TASKS = Estimated completion
Days | Date | Actual Tasks completed
1 | 2018-03-28 |  | Navbar + all db stuff
2 | 2018-03-29 | 0
3 | 2018-03-30 | 0
4 | 2018-03-31 | 0
5 | 2018-04-01 | 0
6 | 2018-04-02 | 0
7 | 2018-04-03 | 0
8 | 2018-04-04 | 0 | <-- 2 weeks later
9 | 2018-04-05 | 0
10 | 2018-04-06 | 0
11 | 2018-04-07 | 0
12 | 2018-04-08 | 0
13 | 2018-04-09 | 0
14 | 2018-04-10 | 0
15 | 2018-04-11 | 0
16 | 2018-04-12 |  | Contact Page
17 | 2018-04-13 | 0
18 | 2018-04-14 | 0
19 | 2018-04-15 | 0
20 | 2018-04-16 | 0
21 | 2018-04-17 | 0 | <-- 9 days or about 1.5 wks later
22 | 2018-04-18 | 0
23 | 2018-04-19 | 0
24 | 2018-04-20 | 0
25 | 2018-04-21 | 0
26 | 2018-04-22 |  | Login/Logout, Contact Function
27 | 2018-04-23 | 0
28 | 2018-04-24 |  | Gallery + Our Team, login design
29 | 2018-04-25 | 0
30 | 2018-04-26 |  | About page finished
31 | 2018-04-27 | 0
32 | 2018-04-28 | 0
33 | 2018-04-29 | TBA
34 | 2018-04-30 | TBA | *Most stories will completed tomorrow if not Tuesday
35 | 2018-05-01 | TBA
36 | 2018-05-02 |  | Workshop 9 Day